## Plan
Plan ID | Plan name | Date of export
3wzVQyBtTEK_SwaVsYEqzZcACTey | R&D Project Management | 2026-10-09

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
NNL7YbUKkk-s3s-_f8hAfJcANCa_ | IM- PLC fundamentals | Production Handover Phase |  | Completed | Important | Maciej Kedzierski;Hamed Adefuwa | Jack Murphy | 2026-02-19 |  | 2024-11-16 |  | false | 2026-02-19 | Jack Murphy | 0/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
L4NkAenkhEKThL2oATGAl5cAMQwg | IM- PLC fundamentals | Production Handover Phase |  | Completed | Important | Maciej Kedzierski;Hamed Adefuwa | Jack Murphy | 2026-02-19 | 2026-03-08 | 2024-10-16 |  | false | 2026-02-19 | Jack Murphy | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
LApSefnZ1kSclY3HLfVxDpcAGkM4 | IM- PLC fundamentals | Production Handover Phase |  | Completed | Important | Maciej Kedzierski;Hamed Adefuwa | Jack Murphy | 2026-02-19 | 2026-02-08 | 2024-09-18 |  | false | 2026-02-19 | Jack Murphy | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
PpFiFZG-TEOkZ9w2EWXW7ZcAOk3T | IM- PLC fundamentals | Production Handover Phase |  | Completed | Important | Maciej Kedzierski;Hamed Adefuwa | Hamed Adefuwa | 2026-02-18 | 2026-01-08 | 2024-08-18 |  | false | 2026-02-19 | Jack Murphy | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
5UmyMdjJPEO5_fMtQyP91pcAHGDW | IM- PLC fundamentals | Production Handover Phase |  | Completed | Important | Maciej Kedzierski;Hamed Adefuwa | Jack Murphy | 2025-09-01 | 2025-12-19 | 2024-07-29 |  | false | 2026-02-18 | Hamed Adefuwa | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
mKuZbSSpbkmnlrwa34wvGpcAO-R5 | IM - Electrical Troubleshooting | Research Phase |  | In progress | Low | Hamed Adefuwa | Jack Murphy | 2025-09-01 |  | 2025-09-08 |  | false |  |  | 1/11 | Curriculum Outline;User Manual;Brief Response Doc;Beta Prototype;Electrical Drawings First Draft;Electrical Test Procedures;Alpha Prototype;Teachers Notes;Electrical Drawings;Spec Doc;PLC Software
M8KSVEgENUydEcfHESEVXJcABFSd | Brief 6.1 - FLOWCODE: DIGITAL COMMUNICATIONS COURSE FOR FLOWCODE | All potential R&D |  | Not started | Low |  | Jack Murphy | 2025-09-01 |  |  |  | false
tlbKUPPqXEypJ6EHCWVihJcAEUux | Wind Tunnel - Gratnell tray updated | Production Based Projects |  | Not started | Medium |  | Jack Murphy | 2025-09-01 |  |  |  | false
ojMCcsMsfE2rwZMZz9o_TJcAKIMo | Brief 6.2 - ELECTRONIC ENGINEERING: E-BLOCKS 2 TECHNOLOGY UPDATE | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-01 |  |  |  | false
4jzs484rA0C8U2O-n-eLFpcAJH_B | Brief 6.26 - Robot Arm V3 | In Progress |  | Not started | Medium | Muhammad Abdullah;Ben Rowland;Jack Murphy | Jack Murphy | 2025-09-01 | 2026-08-14 | 2025-08-15 |  | true |  |  | 2/4 | electrical research;brief review and direction;mechanical research;Raspberry Pi USB Camera - Ensure USB Cable Fits In Base |  | added
5y5l0fIjeE624LD42EA5mZcAD5gR | Structures branding plates | In Progress |  | Completed | Medium | Valerii Pozdeev | Jack Murphy | 2025-09-04 | 2025-10-10 | 2025-09-22 |  | false | 2025-10-13 | Valerii Pozdeev | 4/4 | bom changes;instructions updated;prototypes made;fittted to prototypes |  | structure branding plates to be pushed through to production
OJuB4cNrqU2ahuZsOmJjo5cAPg2I | Process Control Branding Plates | In Progress |  | Completed | Medium | Valerii Pozdeev | Jack Murphy | 2025-09-04 | 2025-10-10 | 2025-09-22 |  | false | 2025-10-13 | Valerii Pozdeev | 5/5 | prototype made;fitted to product;bom changes;Recreating a work instructions;instructions update |  | 2 plates with engraves to be fitted across all process control
TTq9W8owZUOuoltQHmW6Y5cAE3Kz | Metal plates for gutted on forklift | In House projects |  | Completed | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false | 2025-10-30 | Maciej Kedzierski
PAzpS31YjUiR5TTaVxG3SJcAGgBx | Brief 6.3 - ELECTRONIC ENGINEERING: MODERN ELECTRONIC TEST AND MEASUREMENT | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
ksflPH0KxkCE0nFRwqzr75cAKueW | Brief 6.4 - ENGINEERING MEASUREMENT, TEST AND CONTROL | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
DQsTzUJO9k-9g_d2mk8aXJcAJF0C | Brief 6.5 - 6.5 ELECTRICAL ENGINEERING: SMART GRID TECHNOLOGY | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
IMe-aTJf202HR6inv9_WD5cAGdtF | Brief 6.6 - 6.6 MANUFACTURING ENGINEERING: HYDRAULICS | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
qxAmuVLesU2luN08B0i8YpcAPfzC | Brief 6.8 - HYBRID ENGINE INVESTIGATION | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
zKVMMZ3HPUyvulFIMKe_cZcAASp7 | Brief 6.9 - ROBOT ARM: PLC PROGRAMMING | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
kuO0ruJa0EKAuKkcgkll35cAF1LC | Brief 6.10 - TEST ROUTINE PROJECTS | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
Ww9O2SQRvEypD0pDoItLrZcANcOo | Brief 6.12 - HVAC | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
4M4Ti10--UicNjx8h3SNvpcABgNx | Brief 6.13 - Smart Factory 2 | In Progress |  | In progress | Medium | Hamed Adefuwa;Valerii Pozdeev | Jack Murphy | 2025-09-05 | 2026-05-29 | 2025-10-06 |  | true |  |  | 5/14 | Beta Prototype;Electrical Drawings First Draft;Specification Document ;Mechanical Test Procedures ;Alpha Prototype;User Manual;Electrical Test Procedures ;CE Documentation;Electrical Drawings Final;Brief Response Doc;PLC Software;Curriculum Outline ;Teachers Notes;Hydraulic / P&ID Schematic
xpWypIc2Vk2N2zfAGXcO-5cAE-gU | Brief 6.14 - MATERIALS TESTER – UNIVERSAL TESTING MACHINE | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
YcdO1B_YCU-lm6pqE2ec7ZcADgNx | Brief 6.15 - NEW CONTROL APPLICATIONS | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
PJGZwd4qx0SmyUwcqEm92ZcALvzQ | EM Test Jig | Production Based Projects |  | Completed | Important | Maciej Kedzierski;Ben Rowland | Jack Murphy | 2025-09-05 |  |  |  | false | 2025-10-08 | Ben Rowland | 4/4 | Make Jig for Driver board to make it easier to quick connect;Make MDF jig;Hand over to production;Obtain production batch of boards
U0i4wOBB5Ueu9KrPSDGfn5cAPVh5 | 3 Phase Test Jig | Production Based Projects |  | Completed | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false | 2025-09-17 | Jack Murphy
OsJ1HO7BxEiMXSaA9dwGe5cAHygc | Wind Tunnel 9in1 Test Jig | Production Based Projects |  | In progress | Important | Muhammad Abdullah;Valerii Pozdeev | Jack Murphy | 2025-09-05 | 2025-12-23 | 2025-09-26 |  | true |  |  | 6/8 | 3D print;Testing;Assembling;Design;Order parts;Refine;Sign off;SOP documentation
BACudhentEmElbKe8HUZq5cAJ0nP | Thermo - Heat Exchanger | In Progress |  | In progress | Urgent | Paul Connor;Jack Murphy | Jack Murphy | 2025-09-05 | 2025-12-02 | 2021-01-01 |  | true |  |  | 1/3 | Test software UI;Test shell & tube;Test plate exchanger |  | This project is top priority in the team - lots of testing happening.
k3KjG1e6kEeOxodqO_EEhJcAGR6x | Thermo - Heat Conduction | In Progress |  | In progress | Urgent | Muhammad Abdullah;Jack Murphy | Jack Murphy | 2025-09-05 | 2025-08-21 | 2022-01-01 |  | true |  |  | 0/20 | LD0016 - Matrix Pre-Release Product Test;LD0015 – Production Test Procedure;LD0018 – Engineer Final Sign-Off Certificate;LD0012 – Final Prototype Approval Document;LD0011 – Standards Review Checklist;LD0006 – Internal R&D Test Procedure Document;LD0020 – Production Handover Report;LD0017 – Design Archive Checklist;LD0004 – Hazard Analysis;LD0002 – Engineering Response to Brief;LD0010 – Software GUI Completion Checklist;LD0005 – Risk Assessment;LD0021 – Marketing Handover Checklist;LD0013 – CE Technical Document TH4090;LD0008 – Electrical Completion Checklist;LD0019 – Production Handover Checklist;LD0014 – User Manual Checklist;LD0009 – Firmware Completion Checklist;LD0007 – Mechanical Completion Checklist;LD0003 – First Prototype Approval Document
GZMzSLWbmEKZEIEJJQGsfJcACscH | Thermo - Stirling Engine | In Progress |  | In progress | Urgent | Muhammad Abdullah;Maciej Kedzierski;Jack Murphy | Jack Murphy | 2025-09-05 | 2025-09-04 | 2021-01-01 |  | true |  |  | 0/20 | LD0005 - Risk Assessment;LD0015 - Production Test Procedure;LD0009 - Firmware Completion Checklist;LD0002 - Engineering Response to Brief;LD0010 - Software GUI Completion Checklist;LD0019 - Productions Handover Checklist;LD0021 - Marketing Handover Checklist;LD0004 - Hazard Analysis ;LD0013 - CE Technical Document TH4090;LD0003 - First Prototype Approval Document;LD0007 - Mechanical Completion Checklist;LD0016 - Matrix Pre-Release Product Test;LD0017 - Design Archive Checklist;LD0018 - Engineer Final Sign-Off Certificate;LD0014 - User Manual Checklist;LD0008 - Electrical Completion Checklist;LD0006 - Internal R&D Test Procedure Document;LD0020 - Productions Handover Report;LD0011 - Standards Review Checklist;LD0012 - Final Prototype Approval Document
ymv4q1HX9kyyyWG45fAYZJcAHlR1 | IM- Maintenance of Closed Loop | Production Handover Phase |  | Completed | Important | Maciej Kedzierski;Hamed Adefuwa | Jack Murphy | 2025-09-05 | 2025-12-19 | 2024-01-29 |  | false | 2026-02-18 | Hamed Adefuwa | 6/6 | Wiring Diagram;Curriculum Review;Waiting for handover;Build instructions;BOM generated and handed over;Test routine
4Rt0ODhUv0a-wqkvh4vYtJcAKHfc | IM- Logo! PLC | Production Handover Phase |  | Completed | Important | Maciej Kedzierski;Hamed Adefuwa | Jack Murphy | 2025-09-05 | 2025-10-31 | 2024-07-29 |  | false | 2025-10-31 | Hamed Adefuwa | 4/5 | Wiring Diagram;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
fMjkr4Rf9kOk7zGvcATDkZcAFLr2 | Brief 6.16 - OPERATIONAL AMPLIFIERS UPDATE | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
FImdJzhHtkS1tk-WX2nnU5cADK9r | Brief 6.17 - AUTOMATICS CONTROL FIRMWARE FOR MIAC NXT | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
5e2eBS9hYUGL0U5y5-wzb5cAHwTt | Brief 6.18 - LOCKTRONICS PACKS UPDATE | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
Q-m3hBhnlk-WqYGP8YkJvpcAIuoz | Brief 6.19 - ALLEN BRADLEY | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
NsY6AZ2Uq0mgMb2J7Pz5tpcABDDU | DP0077 - Brief 6.20 - PROCESS CONTROL TOUCH SCREEN AND PCB UPDATE | In Progress |  | In progress | Medium | Muhammad Abdullah;Ben Rowland;Valerii Pozdeev | Jack Murphy | 2025-09-05 |  | 2026-01-01 |  | false |  |  | 0/20 | LD0012 – Final Prototype Approval Document;LD0019 – Production Handover Checklist;LD0014 – User Manual Checklist;LD0020 – Production Handover Report;LD0016 - Matrix Pre-Release Product Test;LD0007 – Mechanical Completion Checklist;LD0002 – Engineering Response to Brief;LD0011 – Standards Review Checklist;LD0021 – Marketing Handover Checklist;LD0017 – Design Archive Checklist;LD0005 – Risk Assessment;LD0018 – Engineer Final Sign-Off Certificate;LD0015 – Production Test Procedure;LD0010 – Software GUI Completion Checklist;LD0004 – Hazard Analysis;LD0008 – Electrical Completion Checklist;LD0009 – Firmware Completion Checklist;LD0003 – First Prototype Approval Document;LD0013 – CE Technical Document;LD0006 – Internal R&D Test Procedure Document |  | to update the 5 PC units, with 9in1 pcb and touch screen. we a few small tweaks to improve experiments if required. temperature unit has known experimental length issues. documentation and test routine are critical improvements. doc - report on known issues and improvements we'd like to see
c7IXJRfWR0CSjNLmqAAMQJcAHWi0 | Brief 6.21 - 6.21 FLUIDS CONTROLLER TOUCH SCREEN AND PCB UPDATE | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
wzxZt6TsGE6nPwwL8pI2v5cAOj9G | Brief 6.22 - HP2001 V2 | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
H0z1ZzTC9kGIXt1nc6O6hZcANI6D | Brief 6.24 - MATERIAL TESTING | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
dbSmE-Kkt06yA2W7GRqLgJcAMD-Z | Brief 6.25 - FLUIDS PLUS | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
ws9XepYKmUCGaUIsk0mwqZcAMTIe | Brief 6.27 - VIBRATION MASS DAMPENER | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
4OEma_FwpU2xfq3k2cfP5ZcAGFDl | Brief 6.28 - FLIGHT THEORY | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
OO1uWenPBESXEgCd-WRt2ZcAGGn- | Brief 6.29 - GAS TURBINES | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
wftDtTg_O06btXjrQlMMWZcANZTc | Brief 6.30 - WIND TURBINE GENERATOR | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
JhEytzVabUap1r5I5mX4sJcADaso | Brief 6.31 - DRONE MOTOR TESTER | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
pvD9Pq_OBEyaQLyk99YoEpcAHGIh | Brief 6.32 - IOT/MOBILE DEVICES PACK | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2025-09-05 |  |  |  | false
R5djo4GRpUuySllfXlk2VpcABdmR | Brief 6.33 - PA HILTON DATA LOGGER | In Progress |  | Completed | Important | Paul Connor;Jack Murphy;Liam Walton | Jack Murphy | 2025-09-05 | 2025-10-03 | 2025-08-01 |  | false | 2026-02-19 | Jack Murphy | 9/9 | test on all products;need to find and buy black box without flanges;discuss branding and logistics of shipping;BOM genetrated;test routine to be generated;build instructions;need to update touch screen GUI to only be PA hilton related and on brand too;need to brand the app so it looks like matrix style;make final prototype
3DhTtZAdPU-Roh2_TIXkZZcAOuzI | E-BLOCKS 3 | In Progress |  | Completed | Important | Ben Rowland;Jack Murphy | Jack Murphy | 2025-09-05 | 2026-01-01 | 2025-08-01 |  | false | 2026-02-19 | Jack Murphy | 6/6 | Improve PIC bootloader - current one has problems, MCHP version requires python;Modify the CapTouchDisplay board to have better power distribution when WIFI active;Complete John's GLCD demo project file;review beta prototype design boards;Get BOMs to Jayne for production boards;Review Hamed's comments and investigate problems
v8BTHtyLKU-bb6Pwww3ZUZcAG5xf | MICRO CNC v2 | Research Phase |  | Not started | Low |  | Jack Murphy | 2025-09-05 |  |  |  | false
1zxgl2YSZ0mMGiMooBzr5JcAHnY6 | Touch Screen/App development | Research Phase |  | In progress | Medium | Muhammad Abdullah;Ben Rowland;Paul Connor;Hamed Adefuwa | Jack Murphy | 2025-09-05 |  |  |  | false |  |  | 3/5 | Move drawing routines to sub macros to save on ROM usage?;Add user defined char spacing and space width to binary font support ;Improve Ellipse border drawing;Circular Slider?;review meeting on 6th oct |  | project to denote all the time and research going into the touch screen apps and technology ideas and solutions ben-wsywyg flowcode solution development Abdullah - touchgfx and ST Hamed - PI app's Paul - wsyswyg implementation on a project (PA Hilton)
mAv25HuwpEau_c97lnuLm5cAP0P0 | Lead Acid Battery case | Production Based Projects |  | Completed | Urgent | Valerii Pozdeev | Jack Murphy | 2025-09-05 | 2025-10-03 | 2025-09-23 |  | false | 2025-10-06 | Valerii Pozdeev | 4/4 | BETA;First prototype;Hand project over to Maciej;Alpha |  | This is a top priority
73oN9Dk5cUyfqd_UU_fOZZcAFtyT | HP2001 Doc Updates | In Progress |  | Completed | Low | Muhammad Abdullah;Hamed Adefuwa | Hamed Adefuwa | 2025-09-18 | 2025-02-01 |  |  | false | 2025-10-31 | Hamed Adefuwa |  |  |  | Notes from John: HP2001 has changed. This necessitates some documentation changes. HP2001 is used in conjunction with several products: · LK2410 Motors, generators and charging systems · LK5281 High Voltage and Batteries · LK8170 Fault finding What we need to do is identify all the places HP2001 is used and then modify the worksheets accordingly.
Nq_BHhIjCkWyzrH5Cedy0JcAF96z | IM - IO-Link | In Progress |  | In progress | Low | Maciej Kedzierski;Paul Connor;Hamed Adefuwa | Jack Murphy | 2025-09-26 | 2026-02-17 | 2025-07-01 |  | true |  |  | 0/9 | Drawings First Draft;Define Learning Objectives ;Test Procedures;User Manual;Teachers Notes;Curriculum Outline;Spec Doc;CE Documentation;Software
3-G-UgVF10adaD3xbCsV9ZcAKl3Q | LD0003 - First Prototype Approval Document | In Progress |  | Not started | Medium |  | Maciej Kedzierski | 2026-04-15 |  |  |  | false
TunLCfPWyUuNaJdEWBIeZpcAIfcq | AC-DC Trainer DP0081 | In Progress |  | In progress | Important |  | Paul Connor | 2026-06-25 |  |  |  | false |  |  | 0/20 | LD0005 – Risk Assessment;LD0012 – Final Prototype Approval Document;LD0003 – First Prototype Approval Document;LD0004 – Hazard Analysis;LD0017 – Design Archive Checklist;LD0009 – Firmware Completion Checklist;LD0013 – CE Technical Document;LD0006 – Internal R&D Test Procedure Document;LD0011 – Standards Review Checklist;LD0002 – Engineering Response to Brief;LD0016 - Matrix Pre-Release Product Test;LD0018 – Engineer Final Sign-Off Certificate;LD0020 – Production Handover Report;LD0015 – Production Test Procedure;LD0008 – Electrical Completion Checklist;LD0007 – Mechanical Completion Checklist;LD0010 – Software GUI Completion Checklist;LD0019 – Production Handover Checklist;LD0014 – User Manual Checklist;LD0021 – Marketing Handover Checklist
bNlXvkcelk-PR0Yy8HzIt5cAMtVO | RF for MOD | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2026-07-09 |  |  |  | false
woMXhxL1QEC_44iw0Fsht5cAIYXR | Flowcode eblocks3 ccyber security | All potential R&D |  | Not started | Medium |  | Jack Murphy | 2026-07-09 |  |  |  | false

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
NNL7YbUKkk-s3s-_f8hAfJcANCa_ | IM- PLC fundamentals | pb6dSWzLwE6F_cVEGF-QiJcANUMM |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2026-02-19 |  | 2024-11-16 |  | false | 2026-02-19 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 0/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
L4NkAenkhEKThL2oATGAl5cAMQwg | IM- PLC fundamentals | pb6dSWzLwE6F_cVEGF-QiJcANUMM |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2026-02-19 | 2026-03-08 | 2024-10-16 |  | false | 2026-02-19 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
LApSefnZ1kSclY3HLfVxDpcAGkM4 | IM- PLC fundamentals | pb6dSWzLwE6F_cVEGF-QiJcANUMM |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2026-02-19 | 2026-02-08 | 2024-09-18 |  | false | 2026-02-19 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
PpFiFZG-TEOkZ9w2EWXW7ZcAOk3T | IM- PLC fundamentals | pb6dSWzLwE6F_cVEGF-QiJcANUMM |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 2026-02-18 | 2026-01-08 | 2024-08-18 |  | false | 2026-02-19 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
5UmyMdjJPEO5_fMtQyP91pcAHGDW | IM- PLC fundamentals | pb6dSWzLwE6F_cVEGF-QiJcANUMM |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-01 | 2025-12-19 | 2024-07-29 |  | false | 2026-02-18 | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6/6 | Wiring Diagram;Waiting for handover;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
mKuZbSSpbkmnlrwa34wvGpcAO-R5 | IM - Electrical Troubleshooting | 3g721ev2y0qUkQOxkPh0P5cAK36U |  | In progress | Low | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-01 |  | 2025-09-08 |  | false |  |  | 1/11 | Curriculum Outline;User Manual;Brief Response Doc;Beta Prototype;Electrical Drawings First Draft;Electrical Test Procedures;Alpha Prototype;Teachers Notes;Electrical Drawings;Spec Doc;PLC Software
M8KSVEgENUydEcfHESEVXJcABFSd | Brief 6.1 - FLOWCODE: DIGITAL COMMUNICATIONS COURSE FOR FLOWCODE | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Low |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-01 |  |  |  | false
tlbKUPPqXEypJ6EHCWVihJcAEUux | Wind Tunnel - Gratnell tray updated | p6DoV2qgxUKtW1pZv9IUopcAIB_e |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-01 |  |  |  | false
ojMCcsMsfE2rwZMZz9o_TJcAKIMo | Brief 6.2 - ELECTRONIC ENGINEERING: E-BLOCKS 2 TECHNOLOGY UPDATE | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-01 |  |  |  | false
4jzs484rA0C8U2O-n-eLFpcAJH_B | Brief 6.26 - Robot Arm V3 | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | Not started | Medium | b1624750-7b00-4eab-bc26-bb2767c29fd6;167a9eaa-0218-48f9-bf4f-179bb5420e2f;6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-01 | 2026-08-14 | 2025-08-15 |  | true |  |  | 2/4 | electrical research;brief review and direction;mechanical research;Raspberry Pi USB Camera - Ensure USB Cable Fits In Base |  | added
5y5l0fIjeE624LD42EA5mZcAD5gR | Structures branding plates | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | Completed | Medium | b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-04 | 2025-10-10 | 2025-09-22 |  | false | 2025-10-13 | b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 4/4 | bom changes;instructions updated;prototypes made;fittted to prototypes |  | structure branding plates to be pushed through to production
OJuB4cNrqU2ahuZsOmJjo5cAPg2I | Process Control Branding Plates | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | Completed | Medium | b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-04 | 2025-10-10 | 2025-09-22 |  | false | 2025-10-13 | b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 5/5 | prototype made;fitted to product;bom changes;Recreating a work instructions;instructions update |  | 2 plates with engraves to be fitted across all process control
TTq9W8owZUOuoltQHmW6Y5cAE3Kz | Metal plates for gutted on forklift | kouEzlMSb0OnF0JpRrQXypcAP6gn |  | Completed | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false | 2025-10-30 | 6d567a8c-05f1-4012-868f-733d97486f80
PAzpS31YjUiR5TTaVxG3SJcAGgBx | Brief 6.3 - ELECTRONIC ENGINEERING: MODERN ELECTRONIC TEST AND MEASUREMENT | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
ksflPH0KxkCE0nFRwqzr75cAKueW | Brief 6.4 - ENGINEERING MEASUREMENT, TEST AND CONTROL | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
DQsTzUJO9k-9g_d2mk8aXJcAJF0C | Brief 6.5 - 6.5 ELECTRICAL ENGINEERING: SMART GRID TECHNOLOGY | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
IMe-aTJf202HR6inv9_WD5cAGdtF | Brief 6.6 - 6.6 MANUFACTURING ENGINEERING: HYDRAULICS | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
qxAmuVLesU2luN08B0i8YpcAPfzC | Brief 6.8 - HYBRID ENGINE INVESTIGATION | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
zKVMMZ3HPUyvulFIMKe_cZcAASp7 | Brief 6.9 - ROBOT ARM: PLC PROGRAMMING | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
kuO0ruJa0EKAuKkcgkll35cAF1LC | Brief 6.10 - TEST ROUTINE PROJECTS | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
Ww9O2SQRvEypD0pDoItLrZcANcOo | Brief 6.12 - HVAC | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
4M4Ti10--UicNjx8h3SNvpcABgNx | Brief 6.13 - Smart Factory 2 | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | In progress | Medium | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7;b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2026-05-29 | 2025-10-06 |  | true |  |  | 5/14 | Beta Prototype;Electrical Drawings First Draft;Specification Document ;Mechanical Test Procedures ;Alpha Prototype;User Manual;Electrical Test Procedures ;CE Documentation;Electrical Drawings Final;Brief Response Doc;PLC Software;Curriculum Outline ;Teachers Notes;Hydraulic / P&ID Schematic
xpWypIc2Vk2N2zfAGXcO-5cAE-gU | Brief 6.14 - MATERIALS TESTER – UNIVERSAL TESTING MACHINE | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
YcdO1B_YCU-lm6pqE2ec7ZcADgNx | Brief 6.15 - NEW CONTROL APPLICATIONS | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
PJGZwd4qx0SmyUwcqEm92ZcALvzQ | EM Test Jig | p6DoV2qgxUKtW1pZv9IUopcAIB_e |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;167a9eaa-0218-48f9-bf4f-179bb5420e2f | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false | 2025-10-08 | 167a9eaa-0218-48f9-bf4f-179bb5420e2f | 4/4 | Make Jig for Driver board to make it easier to quick connect;Make MDF jig;Hand over to production;Obtain production batch of boards
U0i4wOBB5Ueu9KrPSDGfn5cAPVh5 | 3 Phase Test Jig | p6DoV2qgxUKtW1pZv9IUopcAIB_e |  | Completed | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false | 2025-09-17 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f
OsJ1HO7BxEiMXSaA9dwGe5cAHygc | Wind Tunnel 9in1 Test Jig | p6DoV2qgxUKtW1pZv9IUopcAIB_e |  | In progress | Important | b1624750-7b00-4eab-bc26-bb2767c29fd6;b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-12-23 | 2025-09-26 |  | true |  |  | 6/8 | 3D print;Testing;Assembling;Design;Order parts;Refine;Sign off;SOP documentation
BACudhentEmElbKe8HUZq5cAJ0nP | Thermo - Heat Exchanger | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | In progress | Urgent | b6109d41-54cc-4423-8c3e-e19106e5dc95;6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-12-02 | 2021-01-01 |  | true |  |  | 1/3 | Test software UI;Test shell & tube;Test plate exchanger |  | This project is top priority in the team - lots of testing happening.
k3KjG1e6kEeOxodqO_EEhJcAGR6x | Thermo - Heat Conduction | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | In progress | Urgent | b1624750-7b00-4eab-bc26-bb2767c29fd6;6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-08-21 | 2022-01-01 |  | true |  |  | 0/20 | LD0016 - Matrix Pre-Release Product Test;LD0015 – Production Test Procedure;LD0018 – Engineer Final Sign-Off Certificate;LD0012 – Final Prototype Approval Document;LD0011 – Standards Review Checklist;LD0006 – Internal R&D Test Procedure Document;LD0020 – Production Handover Report;LD0017 – Design Archive Checklist;LD0004 – Hazard Analysis;LD0002 – Engineering Response to Brief;LD0010 – Software GUI Completion Checklist;LD0005 – Risk Assessment;LD0021 – Marketing Handover Checklist;LD0013 – CE Technical Document TH4090;LD0008 – Electrical Completion Checklist;LD0019 – Production Handover Checklist;LD0014 – User Manual Checklist;LD0009 – Firmware Completion Checklist;LD0007 – Mechanical Completion Checklist;LD0003 – First Prototype Approval Document
GZMzSLWbmEKZEIEJJQGsfJcACscH | Thermo - Stirling Engine | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | In progress | Urgent | b1624750-7b00-4eab-bc26-bb2767c29fd6;6d567a8c-05f1-4012-868f-733d97486f80;6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-09-04 | 2021-01-01 |  | true |  |  | 0/20 | LD0005 - Risk Assessment;LD0015 - Production Test Procedure;LD0009 - Firmware Completion Checklist;LD0002 - Engineering Response to Brief;LD0010 - Software GUI Completion Checklist;LD0019 - Productions Handover Checklist;LD0021 - Marketing Handover Checklist;LD0004 - Hazard Analysis ;LD0013 - CE Technical Document TH4090;LD0003 - First Prototype Approval Document;LD0007 - Mechanical Completion Checklist;LD0016 - Matrix Pre-Release Product Test;LD0017 - Design Archive Checklist;LD0018 - Engineer Final Sign-Off Certificate;LD0014 - User Manual Checklist;LD0008 - Electrical Completion Checklist;LD0006 - Internal R&D Test Procedure Document;LD0020 - Productions Handover Report;LD0011 - Standards Review Checklist;LD0012 - Final Prototype Approval Document
ymv4q1HX9kyyyWG45fAYZJcAHlR1 | IM- Maintenance of Closed Loop | pb6dSWzLwE6F_cVEGF-QiJcANUMM |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-12-19 | 2024-01-29 |  | false | 2026-02-18 | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6/6 | Wiring Diagram;Curriculum Review;Waiting for handover;Build instructions;BOM generated and handed over;Test routine
4Rt0ODhUv0a-wqkvh4vYtJcAKHfc | IM- Logo! PLC | pb6dSWzLwE6F_cVEGF-QiJcANUMM |  | Completed | Important | 6d567a8c-05f1-4012-868f-733d97486f80;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-10-31 | 2024-07-29 |  | false | 2025-10-31 | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 4/5 | Wiring Diagram;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
fMjkr4Rf9kOk7zGvcATDkZcAFLr2 | Brief 6.16 - OPERATIONAL AMPLIFIERS UPDATE | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
FImdJzhHtkS1tk-WX2nnU5cADK9r | Brief 6.17 - AUTOMATICS CONTROL FIRMWARE FOR MIAC NXT | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
5e2eBS9hYUGL0U5y5-wzb5cAHwTt | Brief 6.18 - LOCKTRONICS PACKS UPDATE | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
Q-m3hBhnlk-WqYGP8YkJvpcAIuoz | Brief 6.19 - ALLEN BRADLEY | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
NsY6AZ2Uq0mgMb2J7Pz5tpcABDDU | DP0077 - Brief 6.20 - PROCESS CONTROL TOUCH SCREEN AND PCB UPDATE | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | In progress | Medium | b1624750-7b00-4eab-bc26-bb2767c29fd6;167a9eaa-0218-48f9-bf4f-179bb5420e2f;b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  | 2026-01-01 |  | false |  |  | 0/20 | LD0012 – Final Prototype Approval Document;LD0019 – Production Handover Checklist;LD0014 – User Manual Checklist;LD0020 – Production Handover Report;LD0016 - Matrix Pre-Release Product Test;LD0007 – Mechanical Completion Checklist;LD0002 – Engineering Response to Brief;LD0011 – Standards Review Checklist;LD0021 – Marketing Handover Checklist;LD0017 – Design Archive Checklist;LD0005 – Risk Assessment;LD0018 – Engineer Final Sign-Off Certificate;LD0015 – Production Test Procedure;LD0010 – Software GUI Completion Checklist;LD0004 – Hazard Analysis;LD0008 – Electrical Completion Checklist;LD0009 – Firmware Completion Checklist;LD0003 – First Prototype Approval Document;LD0013 – CE Technical Document;LD0006 – Internal R&D Test Procedure Document |  | to update the 5 PC units, with 9in1 pcb and touch screen. we a few small tweaks to improve experiments if required. temperature unit has known experimental length issues. documentation and test routine are critical improvements. doc - report on known issues and improvements we'd like to see
c7IXJRfWR0CSjNLmqAAMQJcAHWi0 | Brief 6.21 - 6.21 FLUIDS CONTROLLER TOUCH SCREEN AND PCB UPDATE | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
wzxZt6TsGE6nPwwL8pI2v5cAOj9G | Brief 6.22 - HP2001 V2 | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
H0z1ZzTC9kGIXt1nc6O6hZcANI6D | Brief 6.24 - MATERIAL TESTING | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
dbSmE-Kkt06yA2W7GRqLgJcAMD-Z | Brief 6.25 - FLUIDS PLUS | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
ws9XepYKmUCGaUIsk0mwqZcAMTIe | Brief 6.27 - VIBRATION MASS DAMPENER | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
4OEma_FwpU2xfq3k2cfP5ZcAGFDl | Brief 6.28 - FLIGHT THEORY | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
OO1uWenPBESXEgCd-WRt2ZcAGGn- | Brief 6.29 - GAS TURBINES | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
wftDtTg_O06btXjrQlMMWZcANZTc | Brief 6.30 - WIND TURBINE GENERATOR | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
JhEytzVabUap1r5I5mX4sJcADaso | Brief 6.31 - DRONE MOTOR TESTER | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
pvD9Pq_OBEyaQLyk99YoEpcAHGIh | Brief 6.32 - IOT/MOBILE DEVICES PACK | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
R5djo4GRpUuySllfXlk2VpcABdmR | Brief 6.33 - PA HILTON DATA LOGGER | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | Completed | Important | b6109d41-54cc-4423-8c3e-e19106e5dc95;6932b7bc-bfc3-4dc0-8024-1b549ad7410f;4d66d70e-13bf-4797-8d5e-8ddd67905d22 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-10-03 | 2025-08-01 |  | false | 2026-02-19 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 9/9 | test on all products;need to find and buy black box without flanges;discuss branding and logistics of shipping;BOM genetrated;test routine to be generated;build instructions;need to update touch screen GUI to only be PA hilton related and on brand too;need to brand the app so it looks like matrix style;make final prototype
3DhTtZAdPU-Roh2_TIXkZZcAOuzI | E-BLOCKS 3 | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | Completed | Important | 167a9eaa-0218-48f9-bf4f-179bb5420e2f;6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2026-01-01 | 2025-08-01 |  | false | 2026-02-19 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 6/6 | Improve PIC bootloader - current one has problems, MCHP version requires python;Modify the CapTouchDisplay board to have better power distribution when WIFI active;Complete John's GLCD demo project file;review beta prototype design boards;Get BOMs to Jayne for production boards;Review Hamed's comments and investigate problems
v8BTHtyLKU-bb6Pwww3ZUZcAG5xf | MICRO CNC v2 | 3g721ev2y0qUkQOxkPh0P5cAK36U |  | Not started | Low |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false
1zxgl2YSZ0mMGiMooBzr5JcAHnY6 | Touch Screen/App development | 3g721ev2y0qUkQOxkPh0P5cAK36U |  | In progress | Medium | b1624750-7b00-4eab-bc26-bb2767c29fd6;167a9eaa-0218-48f9-bf4f-179bb5420e2f;b6109d41-54cc-4423-8c3e-e19106e5dc95;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 |  |  |  | false |  |  | 3/5 | Move drawing routines to sub macros to save on ROM usage?;Add user defined char spacing and space width to binary font support ;Improve Ellipse border drawing;Circular Slider?;review meeting on 6th oct |  | project to denote all the time and research going into the touch screen apps and technology ideas and solutions ben-wsywyg flowcode solution development Abdullah - touchgfx and ST Hamed - PI app's Paul - wsyswyg implementation on a project (PA Hilton)
mAv25HuwpEau_c97lnuLm5cAP0P0 | Lead Acid Battery case | p6DoV2qgxUKtW1pZv9IUopcAIB_e |  | Completed | Urgent | b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-05 | 2025-10-03 | 2025-09-23 |  | false | 2025-10-06 | b9fc4ef9-bfd2-4242-ba5c-784572d39792 | 4/4 | BETA;First prototype;Hand project over to Maciej;Alpha |  | This is a top priority
73oN9Dk5cUyfqd_UU_fOZZcAFtyT | HP2001 Doc Updates | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | Completed | Low | b1624750-7b00-4eab-bc26-bb2767c29fd6;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 2025-09-18 | 2025-02-01 |  |  | false | 2025-10-31 | 9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 |  |  |  | Notes from John: HP2001 has changed. This necessitates some documentation changes. HP2001 is used in conjunction with several products: · LK2410 Motors, generators and charging systems · LK5281 High Voltage and Batteries · LK8170 Fault finding What we need to do is identify all the places HP2001 is used and then modify the worksheets accordingly.
Nq_BHhIjCkWyzrH5Cedy0JcAF96z | IM - IO-Link | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | In progress | Low | 6d567a8c-05f1-4012-868f-733d97486f80;b6109d41-54cc-4423-8c3e-e19106e5dc95;9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2025-09-26 | 2026-02-17 | 2025-07-01 |  | true |  |  | 0/9 | Drawings First Draft;Define Learning Objectives ;Test Procedures;User Manual;Teachers Notes;Curriculum Outline;Spec Doc;CE Documentation;Software
3-G-UgVF10adaD3xbCsV9ZcAKl3Q | LD0003 - First Prototype Approval Document | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | Not started | Medium |  | 6d567a8c-05f1-4012-868f-733d97486f80 | 2026-04-15 |  |  |  | false
TunLCfPWyUuNaJdEWBIeZpcAIfcq | AC-DC Trainer DP0081 | KSeMrBuTuUCsJBbgZV4mTJcAApbe |  | In progress | Important |  | b6109d41-54cc-4423-8c3e-e19106e5dc95 | 2026-06-25 |  |  |  | false |  |  | 0/20 | LD0005 – Risk Assessment;LD0012 – Final Prototype Approval Document;LD0003 – First Prototype Approval Document;LD0004 – Hazard Analysis;LD0017 – Design Archive Checklist;LD0009 – Firmware Completion Checklist;LD0013 – CE Technical Document;LD0006 – Internal R&D Test Procedure Document;LD0011 – Standards Review Checklist;LD0002 – Engineering Response to Brief;LD0016 - Matrix Pre-Release Product Test;LD0018 – Engineer Final Sign-Off Certificate;LD0020 – Production Handover Report;LD0015 – Production Test Procedure;LD0008 – Electrical Completion Checklist;LD0007 – Mechanical Completion Checklist;LD0010 – Software GUI Completion Checklist;LD0019 – Production Handover Checklist;LD0014 – User Manual Checklist;LD0021 – Marketing Handover Checklist
bNlXvkcelk-PR0Yy8HzIt5cAMtVO | RF for MOD | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2026-07-09 |  |  |  | false
woMXhxL1QEC_44iw0Fsht5cAIYXR | Flowcode eblocks3 ccyber security | s9xgUKRaCk--wAfiKrP6w5cADCzF |  | Not started | Medium |  | 6932b7bc-bfc3-4dc0-8024-1b549ad7410f | 2026-07-09 |  |  |  | false

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
s9xgUKRaCk--wAfiKrP6w5cADCzF | All potential R&D
3g721ev2y0qUkQOxkPh0P5cAK36U | Research Phase
KSeMrBuTuUCsJBbgZV4mTJcAApbe | In Progress
pb6dSWzLwE6F_cVEGF-QiJcANUMM | Production Handover Phase
p6DoV2qgxUKtW1pZv9IUopcAIB_e | Production Based Projects
kouEzlMSb0OnF0JpRrQXypcAP6gn | In House projects

## Users
User ID | User Name | Email
6d567a8c-05f1-4012-868f-733d97486f80 | Maciej Kedzierski | Maciej.Kedzierski@matrixtsl.com
9b9c49c6-53fd-42d4-989a-c7ffae5ebbb7 | Hamed Adefuwa | hamed.adefuwa@matrixtsl.com
6932b7bc-bfc3-4dc0-8024-1b549ad7410f | Jack Murphy | jack.murphy@matrixtsl.com
b1624750-7b00-4eab-bc26-bb2767c29fd6 | Muhammad Abdullah | muhammad.abdullah@matrixtsl.com
167a9eaa-0218-48f9-bf4f-179bb5420e2f | Ben Rowland | ben.rowland@matrixtsl.com
b9fc4ef9-bfd2-4242-ba5c-784572d39792 | Valerii Pozdeev | valerii.pozdeev@matrixtsl.com
b6109d41-54cc-4423-8c3e-e19106e5dc95 | Paul Connor | paul.connor@matrixtsl.com
4d66d70e-13bf-4797-8d5e-8ddd67905d22 | Liam Walton | liam.walton@matrixtsl.com