## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
Nq_BHhIjCkWyzrH5Cedy0JcAF96z | IM - IO-Link | In Progress | In progress | Low | Paul Connor;Hamed Adefuwa;Maciej Kedzierski | Jack Murphy | 26/09/2025 | 01/07/2025 | 17/02/2026 | false | false |  |  | 0/1 | Define Learning Objectives
73oN9Dk5cUyfqd_UU_fOZZcAFtyT | HP2001 Doc Updates | In Progress | In progress | Low | Muhammad Abdullah;Hamed Adefuwa | Hamed Adefuwa | 18/09/2025 |  | 01/02/2025 | false | true | [5 empty] | Notes from John: HP2001 has changed. This necessitates some documentation changes. HP2001 is used in conjunction with several products: · LK2410 Motors, generators and charging systems · LK5281 High Voltage and Batteries · LK8170 Fault finding What we need to do is identify all the places HP2001 is used and then modify the worksheets accordingly.
1zxgl2YSZ0mMGiMooBzr5JcAHnY6 | Touch Screen/App development | Research Phase | In progress | Medium | Muhammad Abdullah;Paul Connor;Ben Rowland;Hamed Adefuwa | Jack Murphy | 05/09/2025 |  |  | false | false |  |  | 3/5 | Move drawing routines to sub macros to save on ROM usage?;Add user defined char spacing and space width to binary font support ;Improve Ellipse border drawing;Circular Slider?;review meeting on 6th oct |  | project to denote all the time and research going into the touch screen apps and technology ideas and solutions ben-wsywyg flowcode solution development Abdullah - touchgfx and ST Hamed - PI app's Paul - wsyswyg implementation on a project (PA Hilton)
v8BTHtyLKU-bb6Pwww3ZUZcAG5xf | MICRO CNC v2 | Research Phase | Not started | Low |  | Jack Murphy | 05/09/2025 |  |  | false | false
3DhTtZAdPU-Roh2_TIXkZZcAOuzI | E-BLOCKS 3 | In Progress | In progress | Important | Ben Rowland;Jack Murphy | Jack Murphy | 05/09/2025 | 01/08/2025 | 01/01/2026 | false | false |  |  | 0/4 | Improve PIC bootloader - current one has problems, MCHP version requires python;Modify the CapTouchDisplay board to have better power distribution when WIFI active;Complete John's GLCD demo project file;Get BOMs to Jayne for production boards
R5djo4GRpUuySllfXlk2VpcABdmR | Brief 6.33 - PA HILTON DATA LOGGER | In Progress | Not started | Important | Paul Connor;Jack Murphy | Jack Murphy | 05/09/2025 | 01/08/2025 | 03/10/2025 | false | true
pvD9Pq_OBEyaQLyk99YoEpcAHGIh | Brief 6.32 - IOT/MOBILE DEVICES PACK | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
JhEytzVabUap1r5I5mX4sJcADaso | Brief 6.31 - DRONE MOTOR TESTER | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
wftDtTg_O06btXjrQlMMWZcANZTc | Brief 6.30 - WIND TURBINE GENERATOR | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
OO1uWenPBESXEgCd-WRt2ZcAGGn- | Brief 6.29 - GAS TURBINES | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
4OEma_FwpU2xfq3k2cfP5ZcAGFDl | Brief 6.28 - FLIGHT THEORY | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
ws9XepYKmUCGaUIsk0mwqZcAMTIe | Brief 6.27 - VIBRATION MASS DAMPENER | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
dbSmE-Kkt06yA2W7GRqLgJcAMD-Z | Brief 6.25 - FLUIDS PLUS | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
H0z1ZzTC9kGIXt1nc6O6hZcANI6D | Brief 6.24 - MATERIAL TESTING | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
wzxZt6TsGE6nPwwL8pI2v5cAOj9G | Brief 6.22 - HP2001 V2 | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
c7IXJRfWR0CSjNLmqAAMQJcAHWi0 | Brief 6.21 - 6.21 FLUIDS CONTROLLER TOUCH SCREEN AND PCB UPDATE | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
NsY6AZ2Uq0mgMb2J7Pz5tpcABDDU | Brief 6.20 - PROCESS CONTROL TOUCH SCREEN AND PCB UPDATE | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
Q-m3hBhnlk-WqYGP8YkJvpcAIuoz | Brief 6.19 - ALLEN BRADLEY | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
5e2eBS9hYUGL0U5y5-wzb5cAHwTt | Brief 6.18 - LOCKTRONICS PACKS UPDATE | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
FImdJzhHtkS1tk-WX2nnU5cADK9r | Brief 6.17 - AUTOMATICS CONTROL FIRMWARE FOR MIAC NXT | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
fMjkr4Rf9kOk7zGvcATDkZcAFLr2 | Brief 6.16 - OPERATIONAL AMPLIFIERS UPDATE | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
4Rt0ODhUv0a-wqkvh4vYtJcAKHfc | IM- Logo! PLC | Production Handover Phase | In progress | Important | Hamed Adefuwa;Maciej Kedzierski | Jack Murphy | 05/09/2025 | 29/07/2024 | 31/10/2025 | false | false |  |  | 4/5 | Wiring Diagram;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
ymv4q1HX9kyyyWG45fAYZJcAHlR1 | IM- Maintenance of Closed Loop | Production Handover Phase | In progress | Important | Hamed Adefuwa;Maciej Kedzierski | Jack Murphy | 05/09/2025 | 29/01/2024 | 31/10/2025 | false | false |  |  | 3/5 | Wiring Diagram;Curriculum Review;Build instructions;BOM generated and handed over;Test routine
GZMzSLWbmEKZEIEJJQGsfJcACscH | Thermo - Stirling Engine | In Progress | In progress | Urgent | Muhammad Abdullah;Maciej Kedzierski | Jack Murphy | 05/09/2025 | 01/01/2021 | 04/09/2025 | false | true
k3KjG1e6kEeOxodqO_EEhJcAGR6x | Thermo - Heat Conduction | In Progress | In progress | Urgent | Muhammad Abdullah | Jack Murphy | 05/09/2025 | 01/01/2022 | 21/08/2025 | false | true
BACudhentEmElbKe8HUZq5cAJ0nP | Thermo - Heat Exchanger | In Progress | In progress | Urgent | Paul Connor;Jack Murphy | Jack Murphy | 05/09/2025 | 01/01/2021 | 02/12/2025 | false | false |  |  | 1/3 | Test software UI;Test shell & tube;Test plate exchanger |  | This project is top priority in the team - lots of testing happening.
OsJ1HO7BxEiMXSaA9dwGe5cAHygc | Wind Tunnel 9in1 Test Jig | Production Based Projects | In progress | Important | Muhammad Abdullah;Valerii Pozdeev | Jack Murphy | 05/09/2025 | 26/09/2025 | 17/10/2025 | false | false |  |  | 2/7 | 3D print;Testing;Assembling;Design;Order parts;Refine;Sign off
YcdO1B_YCU-lm6pqE2ec7ZcADgNx | Brief 6.15 - NEW CONTROL APPLICATIONS | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
xpWypIc2Vk2N2zfAGXcO-5cAE-gU | Brief 6.14 - MATERIALS TESTER – UNIVERSAL TESTING MACHINE | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
4M4Ti10--UicNjx8h3SNvpcABgNx | Brief 6.13 - Smart Factory 2 | Research Phase | Not started | Low | Valerii Pozdeev;Hamed Adefuwa | Jack Murphy | 05/09/2025 | 06/10/2025 | 24/04/2026 | false | false |  |  | 0/3 | Get Robot Arm From Stores (Full Customer Experience);Get Smart Factory From Stores (Full Customer Experience);Run Through Current Curriculum (Full Customer Experience)
Ww9O2SQRvEypD0pDoItLrZcANcOo | Brief 6.12 - HVAC | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
kuO0ruJa0EKAuKkcgkll35cAF1LC | Brief 6.10 - TEST ROUTINE PROJECTS | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
zKVMMZ3HPUyvulFIMKe_cZcAASp7 | Brief 6.9 - ROBOT ARM: PLC PROGRAMMING | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
qxAmuVLesU2luN08B0i8YpcAPfzC | Brief 6.8 - HYBRID ENGINE INVESTIGATION | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
IMe-aTJf202HR6inv9_WD5cAGdtF | Brief 6.6 - 6.6 MANUFACTURING ENGINEERING: HYDRAULICS | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
DQsTzUJO9k-9g_d2mk8aXJcAJF0C | Brief 6.5 - 6.5 ELECTRICAL ENGINEERING: SMART GRID TECHNOLOGY | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
ksflPH0KxkCE0nFRwqzr75cAKueW | Brief 6.4 - ENGINEERING MEASUREMENT, TEST AND CONTROL | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
PAzpS31YjUiR5TTaVxG3SJcAGgBx | Brief 6.3 - ELECTRONIC ENGINEERING: MODERN ELECTRONIC TEST AND MEASUREMENT | All potential R&D | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
TTq9W8owZUOuoltQHmW6Y5cAE3Kz | Metal plates for gutted on forklift | In House projects | Not started | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false
OJuB4cNrqU2ahuZsOmJjo5cAPg2I | Process Control Branding Plates | In Progress | In progress | Medium | Valerii Pozdeev | Jack Murphy | 04/09/2025 | 22/09/2025 | 10/10/2025 | false | false |  |  | 4/5 | prototype made;fitted to product;bom changes;Recreating a work instructions;instructions update |  | 2 plates with engraves to be fitted across all process control
5y5l0fIjeE624LD42EA5mZcAD5gR | Structures branding plates | In Progress | In progress | Medium | Valerii Pozdeev | Jack Murphy | 04/09/2025 | 22/09/2025 | 10/10/2025 | false | false |  |  | 3/4 | bom changes;instructions updated;prototypes made;fittted to prototypes |  | structure branding plates to be pushed through to production
4jzs484rA0C8U2O-n-eLFpcAJH_B | Brief 6.26 - Robot Arm V3 | Research Phase | Not started | Medium | Muhammad Abdullah;Ben Rowland;Jack Murphy | Jack Murphy | 01/09/2025 | 15/08/2025 | 14/08/2026 | false | false |  |  | 0/3 | electrical research;brief review and direction;mechanical research
ojMCcsMsfE2rwZMZz9o_TJcAKIMo | Brief 6.2 - ELECTRONIC ENGINEERING: E-BLOCKS 2 TECHNOLOGY UPDATE | All potential R&D | Not started | Medium |  | Jack Murphy | 01/09/2025 |  |  | false | false
tlbKUPPqXEypJ6EHCWVihJcAEUux | Wind Tunnel - Gratnell tray updated | Production Based Projects | Not started | Medium |  | Jack Murphy | 01/09/2025 |  |  | false | false
M8KSVEgENUydEcfHESEVXJcABFSd | Brief 6.1 - FLOWCODE: DIGITAL COMMUNICATIONS COURSE FOR FLOWCODE | All potential R&D | Not started | Low |  | Jack Murphy | 01/09/2025 |  |  | false | false
5UmyMdjJPEO5_fMtQyP91pcAHGDW | IM- PLC fundamentals | Production Handover Phase | In progress | Important | Hamed Adefuwa;Maciej Kedzierski | Jack Murphy | 01/09/2025 | 29/07/2024 | 31/10/2025 | true | false |  |  | 3/5 | Wiring Diagram;Build instructions;BOM generated and handed over;Test routine;Curriculum Review
mKuZbSSpbkmnlrwa34wvGpcAO-R5 | IM - Electrical Troubleshooting | Research Phase | In progress | Low | Hamed Adefuwa | Jack Murphy | 01/09/2025 | 08/09/2025 |  | false | false
PJGZwd4qx0SmyUwcqEm92ZcALvzQ | EM Test Jig | Production Based Projects | Completed | Important | Ben Rowland;Maciej Kedzierski | Jack Murphy | 05/09/2025 |  |  | false | false | 08/10/2025 | Ben Rowland | 4/4 | Make Jig for Driver board to make it easier to quick connect;Make MDF jig;Hand over to production;Obtain production batch of boards
mAv25HuwpEau_c97lnuLm5cAP0P0 | Lead Acid Battery case | Production Based Projects | Completed | Urgent | Valerii Pozdeev | Jack Murphy | 05/09/2025 | 23/09/2025 | 03/10/2025 | false | false | 06/10/2025 | Valerii Pozdeev | 4/4 | BETA;First prototype;Hand project over to Maciej;Alpha |  | This is a top priority
U0i4wOBB5Ueu9KrPSDGfn5cAPVh5 | 3 Phase Test Jig | Production Based Projects | Completed | Medium |  | Jack Murphy | 05/09/2025 |  |  | false | false | 17/09/2025 | Jack Murphy

## Plan name
Plan name | R&D Project Management
Plan ID | 3wzVQyBtTEK_SwaVsYEqzZcACTey
Date of export | 10/10/2025